## Features
Project: Recall AI
Team: 7
ID | Feature Name | Description | Remark
UC-01 | Register account | Allows new users to create a personal account in the system by submitting required registration details, including full name, email address, and a secure password. | Requires email uniqueness across the platform. Passwords must comply with minimum security requirements (at least 8 characters). Upon successful registration, the system automatically logs the user in and redirects them to the main dashboard.
UC-02 | Login | Enables existing registered users to authenticate into the system using their registered email and password to access protected features and personal data | Displays generic error messages (e.g., 'Invalid email or password') upon authentication failure to prevent user enumeration. Supports session persistence and automatic token renewal.
UC-03 | Personal Profile Management | View and update profile information, including display name, email, join date, and password. | Email is read-only; valid updates persist and sessions remain isolated.
UC-04 | Logout | End the authenticated session and prevent access to protected routes after logout. | Clears the local access token and prevents reuse of prior-session data.

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01: Register account
UC-01 | TC-AM-01-01 | Register successfully with valid data | 1. Open Postman, create request POST /api/v1/auth/register. 2. Set Header: Content-Type: application/json. 3. Enter request body: email "newuser@example.com", password "SecurePass1", name "Nguyen Van A". 4. Send the request. 5. Check the HTTP status code. 6. Check the response body. | - HTTP Status: 201 Created - Response body has "success": true - data.user has correct id, email, name - data.accessToken is a non-empty JWT string - data.refreshToken is a non-empty JWT string - password does not appear in the response - Database has a new user record with the above email | HTTP 201 Created. success: true. data.user has exactly 3 fields (id, email, name). accessToken and refreshToken are valid JWTs. password is not exposed in the response. | Pass | NMPhat | 2026-07-24 | Main happy path. If this TC fails, other UC-01 TCs may not run.
UC-01 | TC-AM-01-02 | Register fails when email already exists | 1. Open Postman, create request POST /api/v1/auth/register. 2. Set Header: Content-Type: application/json. 3. Enter request body with an existing email. 4. Send the request. 5. Check the HTTP status code. 6. Check the response body and error code. | - HTTP Status: 409 Conflict - Response body has "success": false - error.code = "EMAIL_CONFLICT" - error.message contains the existing-email error message - No new record is created in the DB | HTTP 409 Conflict. success: false. error.code: "EMAIL_CONFLICT". error.message describes the existing email error. No duplicate record created in DB. | Pass | NMPhat | 2026-07-24 | Important: also check the DB to confirm no duplicate record was created.
UC-01 | TC-AM-01-03 | Register fails when password < 8 characters | 1. Open Postman, create request POST /api/v1/auth/register. 2. Set Header: Content-Type: application/json. 3. Enter request body with a 7-character password. 4. Send the request. 5. Check the HTTP status code. 6. Check the response body. | - HTTP Status: 400 Bad Request - Response body has "success": false - error.code = "VALIDATION_ERROR" - error.details contains the password field error - No record is created in the DB | HTTP 400 Bad Request. success: false. error.code: "VALIDATION_ERROR". error.details specifies the password field does not meet the minimum length. | Pass | NMPhat | 2026-07-24 | Boundary test: password exactly 7 chars (<8). Should also test exactly 8 chars -> should Pass (see TC-AM-01-01).
UC-01 | TC-AM-01-04a-d | Register fails when email format is invalid (4 cases) | Test set split into 4 independent sub-cases (04a-04d): - 04a: "spaces in@email.com" (contains space) - 04b: "notanemail" (missing @) - 04c: "missing@" (missing domain) - 04d: "@nodomain.com" (missing local part) 1. Open Postman, create request POST /api/v1/auth/register. 2. Set Header: Content-Type: application/json. 3. Enter request body with the invalid email. 4. Send the request. 5. Check the HTTP status code. 6. Check the response body. | For each invalid email: - HTTP Status: 400 Bad Request - "success": false - error.code = "VALIDATION_ERROR" - error.details contains the email field error - No record is created in the DB | All 4 sub-cases returned HTTP 400 Bad Request. success: false. error.code: "VALIDATION_ERROR". error.details specifies the email field is invalid. | Pass (4/4) | NMPhat | 2026-07-24 | Test set split into 4 separate .request.yaml files (04a-04d) for more detailed reporting.
UC-01 | TC-AM-01-05a-d | Register fails when a required field is missing (4 cases) | Test set split into 4 independent sub-cases (05a-05d): - 05a: missing email - 05b: missing password - 05c: missing name - 05d: empty body {} 1. Open Postman, create request POST /api/v1/auth/register. 2. Set Header: Content-Type: application/json. 3. Send bodies missing a field (each case). 4. Check the HTTP status code and response. | For each case: - HTTP Status: 400 Bad Request - "success": false - error.code = "VALIDATION_ERROR" - error.details states which field is missing | All 4 sub-cases returned HTTP 400 Bad Request. success: false. error.code: "VALIDATION_ERROR". error.details specifies the missing field for each case. | Pass (4/4) | NMPhat | 2026-07-24 | Test set split into 4 separate .request.yaml files (05a-05d) for more detailed reporting.
UC-01 | TC-AM-01-06 | Register fails when name < 2 characters | 1. Open Postman, create request POST /api/v1/auth/register. 2. Set Header: Content-Type: application/json. 3. Enter request body with a 1-character name. 4. Send the request and check the response. | - HTTP Status: 400 Bad Request - "success": false - error.code = "VALIDATION_ERROR" - error.details contains the name field error | HTTP 400 Bad Request. success: false. error.code: "VALIDATION_ERROR". error.details specifies name is below the 2-character minimum. | Pass | NMPhat | 2026-07-24 | Boundary test: name = 1 char (fail) vs name = 2 chars (pass).
UC-01 | TC-AM-01-07 | Register success - validate response schema | 1. Send a successful Register request with valid data. 2. Check each field in the response body: a. success is boolean true b. data.user.id is a string (UUID format) c. data.user.email matches the input email d. data.user.name matches the input name e. data.accessToken is a non-empty string f. data.refreshToken is a non-empty string 3. Check the response does NOT contain a password or passwordHash field. | - HTTP Status: 201 Created - data.user has exactly 3 fields: id, email, name - data.user.password does not exist - data.accessToken and data.refreshToken are valid JWTs (header/payload decodable) | HTTP 201 Created. data.user has exactly 3 fields id, email, name. password and passwordHash are not present in the response. accessToken and refreshToken are valid JWTs. | Pass | NMPhat | 2026-07-24 | Security check: the password must never be exposed in the response.
UC-01 | TC-AM-01-08 | Register fails when password is whitespace only | 1. Send a Register request with an 8-character whitespace-only password. 2. Check the HTTP status and response. | - HTTP Status: 400 Bad Request (should be rejected for security reasons) | HTTP 400 Bad Request. The server rejects requests with whitespace-only passwords and returns a validation error. | Pass | NMPhat | 2026-07-29 | Zod validator successfully rejects whitespace-only passwords using `trim()` / whitespace validation.
UC-01 | TC-AM-01-UI-01 | Successful registration with valid data on UI | 1. Open the registration page on a browser 2. Enter Full Name: Nguyen Van A 3. Enter Email: testuser01@example.com 4. Enter Password: Password123! 5. Enter Confirm Password: Password123! 6. Click the Register button | - Registration successful, displays a success Toast/Notification - Automatically redirects to the Dashboard page (or Login page) | Registration successful, system automatically redirects to the Dashboard page | Pass | NMPhat | 2026-07-24 | Main happy path for the UI Register flow.
UC-01 | TC-AM-01-UI-02 | Registration failed when the email already exists in the system (UI) | 1. Open the registration page 2. Enter Full Name: Nguyen Van B, Email: testuser01@example.com (already exists), Password: Password123! 5. Click the Register button | - UI displays a clear error message: "Email đã được đăng ký" or "Email already exists" - Does not redirect, keeps form data intact | Displays a toast message in the bottom right corner: "Email already exists". Stays on the registration form. | Pass | NMPhat | 2026-07-24 | Similar to TC-AM-01-02 at the API level; this TC confirms the UI handles the error response from the Backend correctly.
UC-01 | TC-AM-01-UI-03 | Registration failed when password length is less than 8 characters (UI) | 1. Open the registration page 2. Enter Full Name: Nguyen Van C, Email: test02@example.com, Password: Pass123 (7 chars) 5. Confirm Password: Pass123 6. Click the Register button | - Displays an inline error below the password field: "Mật khẩu phải có ít nhất 8 ký tự" / "Password must be at least 8 characters" - The Register button is disabled or request sending is blocked | Displays an inline error below the Password field: "Password must be at least 8 characters". | Pass | NMPhat | 2026-07-24 | Validation occurs at the Frontend (client-side), no request is sent to the Backend.
UC-01 | TC-AM-01-UI-04 | Registration failed with invalid email format (UI) | 1. Open the registration page 2. Try the invalid email formats sequentially in the Email field 3. Click outside the input field (Blur) or click the Register button | Displays inline error message: "Email không hợp lệ" / "Invalid email address" | When entering invalid emails (e.g., user@), the system displays an inline error message below the Email field: "Invalid email address". | Pass | NMPhat | 2026-07-24 | Tested 4 invalid formats: - user@ - user@com - user.com - user@domain..com Validation occurs at the Frontend.
UC-01 | TC-AM-01-UI-05 | Registration failed when username length is less than 2 characters (UI) | 1. Open the registration page 2. Enter Full Name: A (1 char), Email: testname@example.com, Password: Password123! 3. Click the Register button | Displays error message: "Tên phải có ít nhất 2 ký tự" / "String must contain at least 2 character(s)" | Displays inline error message below the Full Name field: "Name must be at least 2 characters". | Pass | NMPhat | 2026-07-24 | Boundary test: name = 1 char → fail
UC-01 | TC-AM-01-UI-06 | Registration failed when confirm password does not match (UI) | 1. Open the registration page 2. Enter Password: Password123!, Confirm Password: DifferentPass123! 3. Click the Register button | Displays inline error message: "Mật khẩu xác nhận không trùng khớp" / "Passwords do not match" | Displays inline error message below the Confirm Password field: "Passwords do not match". | Pass | NMPhat | 2026-07-24 | This validation is only at the Frontend
Function 02: Login
UC-02 | TC-AM-02-01 | Login successfully with valid data | 1. Open Postman, create request POST /api/v1/auth/login. 2. Set Header: Content-Type: application/json. 3. Enter request body: email "logintest@example.com", password "SecurePass1". 4. Send the request. 5. Check the HTTP status code. 6. Check the response body and save accessToken for subsequent test cases. | - HTTP Status: 200 OK - Response body has "success": true - data.user has id, email, name - data.accessToken is a valid JWT string - data.refreshToken is a valid JWT string - password does not appear in the response | HTTP 200 OK. success: true. data.user has id, email, name. accessToken and refreshToken are valid JWTs. password not exposed in the response. Script automatically saved tokens to Postman Environment. | Pass | NMPhat | 2026-07-24 | Save accessToken & refreshToken from the response - done automatically by the script into the Postman Environment for use in subsequent test cases.
UC-02 | TC-AM-02-02 | Login fails with wrong password | 1. Open Postman, create request POST /api/v1/auth/login. 2. Set Header: Content-Type: application/json. 3. Enter request body with the correct email but wrong password. 4. Send the request. 5. Check the HTTP status code and response. | - HTTP Status: 401 Unauthorized - Response body has "success": false - error.code = "UNAUTHORIZED" - error.message = "Email or password incorrect" (generic message, does not reveal which is wrong) - Response contains no token | HTTP 401 Unauthorized. success: false. error.code: "UNAUTHORIZED". error.message: "Email or password incorrect" - a generic message that does not distinguish the cause, preventing a User Enumeration Attack. | Pass | NMPhat | 2026-07-24 | Security check: the error message must match TC-AM-02-03 exactly to prevent User Enumeration. Confirmed both messages are identical.
UC-02 | TC-AM-02-03 | Login fails when email does not exist | 1. Open Postman, create request POST /api/v1/auth/login. 2. Set Header: Content-Type: application/json. 3. Enter request body with a non-existent email. 4. Send the request. 5. Check the HTTP status code and response. | - HTTP Status: 401 Unauthorized - "success": false - error.code = "UNAUTHORIZED" - error.message = "Email or password incorrect" (identical to TC-AM-02-02) - Response contains no token | HTTP 401 Unauthorized. success: false. error.code: "UNAUTHORIZED". error.message: "Email or password incorrect" - identical to TC-AM-02-02, confirming the server does not distinguish wrong email from wrong password. | Pass | NMPhat | 2026-07-24 | Critical security check: TC-AM-02-02 and TC-AM-02-03 messages are completely identical - confirmed no User Enumeration vulnerability.
UC-02 | TC-AM-02-04 | Access protected route without a token | 1. Open Postman, create request GET /api/v1/auth/me. 2. Do NOT add an Authorization header. 3. Send the request. 4. Check the HTTP status code and response. | - HTTP Status: 401 Unauthorized - "success": false - error.code = "UNAUTHORIZED" - error.message = "Token not provided" (or equivalent) | HTTP 401 Unauthorized. success: false. error.code: "UNAUTHORIZED". Auth middleware blocked the request successfully before it reached the handler logic. | Pass | NMPhat | 2026-07-24 | Also test the case where the Authorization header is present but empty.
UC-02 | TC-AM-02-05 | Access protected route with an expired token | 1. Open Postman, create request GET /api/v1/auth/me. 2. Add header: Authorization: Bearer <expired_token>. 3. Send the request. 4. Check the HTTP status code and response. | - HTTP Status: 401 Unauthorized - "success": false - error.code = "UNAUTHORIZED" - error.message = "Invalid or expired token" | HTTP 401 Unauthorized. success: false. error.code: "UNAUTHORIZED". error.message: "Invalid or expired token". Middleware successfully rejected the expired token. | Pass | NMPhat | 2026-07-24 | The fake token is hardcoded directly in the test file to ensure test stability (not dependent on wait time).
UC-02 | TC-AM-02-06a-c | Login fails when a required field is missing (3 cases) | Case A: {"email": "logintest@example.com"} (missing password) Case B: {} (empty body) Case C: {"password": "SecurePass1"} (missing email) 1. Open Postman, create request POST /api/v1/auth/login. 2. Set Header: Content-Type: application/json. 3. Enter body missing a field (per case). 4. Send the request and check the response. | - HTTP Status: 400 Bad Request - "success": false - error.code = "VALIDATION_ERROR" - error.details states which field is missing | All 3 sub-cases returned HTTP 400 Bad Request. success: false. error.code: "VALIDATION_ERROR". error.details specifies the missing field for each case. | Pass (3/3) | NMPhat | 2026-07-24
UC-02 | TC-AM-02-07 | Access protected route with a valid token | 1. Open Postman, create request GET /api/v1/auth/me. 2. Add header: Authorization: Bearer <valid_access_token>. 3. Send the request. 4. Check the HTTP status code and response body. | - HTTP Status: 200 OK - "success": true - data.id matches the logged-in user - data.email = "logintest@example.com" - data.name matches the registered name - data.password does not appear | HTTP 200 OK. success: true. data.email: "logintest@example.com". data.name and data.id present. password not exposed in the response. | Pass | NMPhat | 2026-07-24 | Confirms the end-to-end flow: Register -> Login -> Use token.
UC-02 | TC-AM-02-08 | Refresh Token succeeds | 1. Open Postman, create request POST /api/v1/auth/refresh. 2. Set Header: Content-Type: application/json. 3. Enter request body with the refreshToken from TC-AM-02-01. 4. Send the request. 5. Check the HTTP status code and response. 6. Confirm the new accessToken differs from the old one. | - HTTP Status: 200 OK - "success": true - data.accessToken is a new, valid JWT - data.accessToken differs from the old accessToken | HTTP 200 OK. success: true. A new accessToken was issued successfully and differs from the old token (thanks to a 1s pre-request delay). | Pass | NMPhat | 2026-07-24 | Use the new accessToken from this test to call GET /api/v1/auth/me again - should return 200. A 1s delay before generating the token avoids duplicate tokens caused by tests running too fast.
UC-02 | TC-AM-02-09a-b | Refresh Token fails with an invalid token (2 cases) | 09a - Fake token: {"refreshToken": "invalid.token.string"} -> expect 401 09b - Missing field: {} -> expect 400 VALIDATION_ERROR (Zod blocks before Auth middleware) 1. Open Postman, create request POST /api/v1/auth/refresh. 2. Set Header: Content-Type: application/json. 3. Enter the invalid body. 4. Send the request and check the response. | 09a: HTTP 401, error.code: "UNAUTHORIZED", error.message: "Invalid or expired refresh token" 09b: HTTP 400, error.code: "VALIDATION_ERROR", error.details states refreshToken is missing | 09a: HTTP 401 Unauthorized. error.code: "UNAUTHORIZED". error.message: "Invalid or expired refresh token". Pass. 09b: HTTP 400 Bad Request. error.code: "VALIDATION_ERROR". error.details: refreshToken expected string, received undefined. Pass. | Pass (2/2) | NMPhat | 2026-07-24 | Design note: Case B (empty body) returns 400, not 401, because Zod validation at the middleware layer blocks the request before it reaches Auth logic. This is correct RESTful design behavior - the test was adjusted to reflect actual behavior.
UC-02 | TC-AM-02-10a-c | Protected route with malformed Bearer token (3 cases) | Sub-cases: - 10a: wrong prefix, "Authorization: Token {{accessToken}}" - 10b: missing "Bearer" prefix (raw token) - 10c: fake token, "Authorization: Bearer fake.token.xyz" 1. Open Postman, create request GET /api/v1/auth/me. 2. Test each incorrect way of passing the token. 3. Check the HTTP status code and response. | For each case: - HTTP Status: 401 Unauthorized - "success": false - error.code = "UNAUTHORIZED" | All 3 sub-cases returned HTTP 401 Unauthorized. success: false. error.code: "UNAUTHORIZED". Middleware rejected the malformed Bearer token. | Pass (3/3) | NMPhat | 2026-07-24 | Test set split into 3 separate .request.yaml files (10a-10c) for more detailed reporting.
UC-02 | TC-AM-02-UI-01 | Successful login with a valid account on UI | 1. Open the login page 2. Enter Email: testuser01@example.com 3. Enter Password: Password123! 4. Click the Login button | - Successful login, redirects to Dashboard / homepage - Username (Nguyen Van A) or Avatar is displayed in the Header/Sidebar | Successful login, system displays a toast notification "Signed in successfully!" in the bottom right corner and automatically redirects to the Dashboard page | Pass | NMPhat | 2026-07-24 | Main happy path for the UI Login flow.
UC-02 | TC-AM-02-UI-02 | Login failed with correct email but wrong password (UI) | 1. Open the login page 2. Enter Email: testuser01@example.com, Password: WrongPassword999! 3. Click the Login button | - Display a generic error message: "Email hoặc mật khẩu không chính xác" (avoiding specific details like "Incorrect password" for security) - Deny access to the Dashboard | - Display error message: "Email or password incorrect" - Stay in login page | Pass | NMPhat | 2026-07-24 | Displayed error message is identical → specific cause is not revealed (User Enumeration prevention).
UC-02 | TC-AM-02-UI-03 | Login failed when logging in with an email not present in the system (UI) | 1. Open the login page 2. Enter Email: notfound_user999@example.com, Password: Password123! 3. Click the Login button | Display error message: "Email hoặc mật khẩu không chính xác" (Email or password incorrect) | Displays error toast message in the bottom right corner: "Email or password incorrect". Login denied. | Pass | NMPhat | 2026-07-24 | Compare with TC-AM-02-UI-02 (Wrong password): displayed error message is identical → specific cause is not revealed (User Enumeration prevention).
UC-02 | TC-AM-02-UI-04 | Login failed when required fields are left empty (UI) | - Case A: Leave Email empty, enter valid Password → Click Login - Case B: Enter valid Email, leave Password empty → Click Login | - Display error: "Vui lòng nhập Email / Mật khẩu" (Please enter Email / Password) - System does not send request to backend | - Case A (Empty Email): Displays inline error immediately below the Email field: "Email is required". - Case B (Empty Password): Displays inline error immediately below the Password field: "Password must be at least 8 characters". - System blocks submit and does not send request to backend. | Pass | NMPhat | 2026-07-24 | Verified both cases A & B. Validation is at the Frontend level.
Function 03: Personal Profile Management
UC-03 | TC-AM-03-01 | Display the correct information for the currently signed-in learner | Prerequisites: The primary learner is logged in; both named and unnamed states can be checked. Test Data: a) Account with a display name. b) Account without a display name. Steps: 1. Open Profile. 2. Observe the name, email, join date, and locked-email state. 3. Reload in both name states. | a) The saved name is shown. b) The name field is empty and is not replaced with the email. The current learner's email and join date appear, and the email cannot be edited. | a) Pass on Chromium and Firefox: the profile correctly displayed the current learner's name, email, and join date; the values remained after reload. b) Pass on Chromium and Firefox: an unnamed account showed the empty field and the correct prompt, without replacing it with the email. | Pass | NMPhat | 2026-09-03 | The learner can verify the account identity and still recognize the profile state when no name has been set.
UC-03 | TC-AM-03-02 | Save a valid name and allow the name to be left blank | Prerequisites: The learner is logged in and Profile is open. Test Data: a) Ngọc An. b) Ngọc An . c) Empty string. Steps: 1. Enter a name and save. 2. Reload and open Dashboard. 3. Clear the name and save again. | a/b) The name is normalized, remains after reload, and appears on Dashboard. c) The name is deleted; Dashboard does not concatenate the email as a name, and the profile email is unchanged. | a/b) Pass on Chromium and Firefox: the valid name was normalized, persisted after reload, and appeared on Dashboard. c) Pass on Chromium and Firefox: the name was successfully cleared and the greeting did not include the email. | Pass | NMPhat | 2026-09-03 | The display name is synchronized between Profile and Dashboard, keeping the greeting consistent without exposing the email as a substitute for the name.
UC-03 | TC-AM-03-03 | Change the password only when the data is valid | Prerequisites: The learner has a valid current password and has opened the Change Password tab. Test Data: a) Correct current password; new password of 8+ characters with matching confirmation. b) Incorrect current password. c) Short new password or different confirmation. Steps: 1. Enter the three password fields. 2. Submit the change. 3. Log out and log in again to verify. | a) Change succeeds; only the new password can log in. b) An incorrect-current-password error is shown; data is not changed. c) A field error is shown and the change is not submitted. | a) Pass on Chromium and Firefox: the valid password was changed successfully and could be used to log in again. b) Pass on Chromium and Firefox: an incorrect old password returned 400 and the password did not change. c) Pass on Chromium and Firefox: mismatched confirmation/insufficient length was blocked by the UI. | Pass | NMPhat | 2026-09-03 | Input checks protect the account from unintended password changes and accept only valid authentication information.
Function 04: Logout
UC-04 | TC-AM-04-01 | Logout redirects to Login and clears the local session | Prerequisites: The learner is logged in and Profile is open. Test Data: Valid logged-in session. Steps: 1. Click Logout. 2. Observe the destination page. 3. Reload. | Redirect to Login; the old session state is gone after reload. | Pass on Chromium and Firefox: logout returned to Login and removed the access token; reload and protected routes did not reopen the session. | Pass | NMPhat | 2026-09-03 | The post-logout path is clear, so the learner knows the session ended and does not accidentally use the old account.
UC-04 | TC-AM-04-02 | Do not access Dashboard or Profile again after logout | Prerequisites: Logout has been completed. Test Data: Protected URLs after the session has been removed. Steps: 1. Open Dashboard. 2. Open Profile. 3. Use Back. | Each action returns to Login without exposing the name, email, or learning data. | Pass on Chromium and Firefox: after logout, /dashboard and /profile both redirected to Login; going back in history did not restore access. | Pass | NMPhat | 2026-09-03 | Protected routes remain secured after logout, so personal data is not exposed by reopening a URL or using browser history.
UC-04 | TC-AM-04-03 | Re-login does not use the previous learner's cache | Prerequisites: Two accounts with different emails/names are available. Test Data: Two independent accounts with different emails and display names. Steps: 1. Log out the first learner. 2. Log in as the second learner. 3. Open Profile and Dashboard. | The new session belongs only to the second learner; no email, name, or private data of the first learner remains. | Pass on Chromium and Firefox: after the first learner logged out and the second logged in, Profile showed only the second learner's data, with no email/name from the first learner. | Pass | NMPhat | 2026-09-03 | Session isolation ensures that shared devices or account switching do not mix learners' personal data.