## Test summary report
Tester | Nguyen Minh Phat, Nguyen The Quan
Date | 14/08/2026

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Registration API allows passwords with only spaces | The registration API accepts passwords consisting of eight space characters and successfully creates an account, weakening password strength requirements. | UC-01 | High | Nguyen Minh Phat | 2026-07-25 | Closed | Need to add a validation rule to block passwords containing only spaces.
B002 | Login screen hangs when API returns invalid password | During initial testing, the loading state on the login form did not end after entering an incorrect password, causing the user to not receive a clear error response. | UC-02 | Medium | Nguyen Minh Phat | 2026-07-25 | Closed | Cannot reproduce during re-testing; need to continue monitoring the 401 error handling branch.
B003 | Concurrent retries can create duplicate jobs or permanently lock retries | The state transitions of AnalysisJob are non-atomic read-then-write operations. Two concurrent retry requests can create or process a duplicate job; a stuck processing job can also cause all subsequent retries to permanently return 409. | UC-05 | High | Nguyen The Quan | 2026-07-31 | Closed | There is a risk of duplicate data creation and retry locking; need atomic claim/retry operations.
B004 | Upload accepts encrypted PDF but Gemini cannot analyze it | The upload middleware only checks MIME type and size, thus passing PDFs with /Encrypt. The file can still be opened by a PDF reader, but the Gemini File API cannot read any pages, causing the analysis job to retry fruitlessly before failing. | UC-05 | Medium | Nguyen The Quan | 2026-08-01 | Closed | Should reject encrypted PDFs immediately upon upload to avoid useless analysis retries.
B005 | PlanDetailPage displays the deadline one day later | The deadline is consistently displayed in the Plan list but increases by one day on the detail screen, resulting in incorrect deadline information for the user. | UC-07 | Medium | Nguyen Minh Phat | 2026-08-02 | Closed | Need to unify the timezone handling to prevent the deadline date from shifting.
B006 | Plan creation API rejects files exactly 10 MB in size | The upload size constraint handles the boundary value incorrectly: a file exactly 10 MiB is rejected, even though the 10 MB limit should include <= 10 MB. | UC-05 | Medium | Nguyen Minh Phat | 2026-08-02 | Closed | The size limit condition must include the exact value of 10 MiB.
B007 | Concept search by name does not work when all concepts are untested | The search-by-name function on the concept graph has no effect when all concepts in the plan have mastery_score = null. | UC-17 | High | Nguyen The Quan | 2026-08-02 | Closed | Need to separate the name search condition from the mastery score filtering condition.
B008 | Post-session score must be inferred from the turns of that session itself, not reading Concept.masteryScore | The summary of an old session retrieves Concept.masteryScore at the time of reopening instead of the score generated by the answers in that specific session, causing the history to display incorrect data. | UC-18 | Medium | Nguyen The Quan | 2026-08-05 | Closed | Historical scores must be calculated from the answering turns of that specific session.
B009 | Plan switches to active immediately after analysis is complete, bypassing the graph verification step | After the analysis job completes, the plan is immediately switched to active. As a result, the graph verification screen, which only shows when the plan is draft, never appears. | UC-06 | High | Nguyen The Quan | 2026-08-06 | Closed | Only activate the plan after the user confirms the concept graph.
B010 | State Machine does not Traceback / Spaced Repetition on incorrect answer | When a student completely answers incorrectly (0.00, verdict wrong), the State Machine still asks the next question for the same concept instead of switching to the Traceback or Spaced Repetition flow. | UC-13 | High | Nguyen Minh Phat | 2026-08-06 | Closed | Need to properly trigger Traceback or Spaced Repetition upon a completely wrong answer.
B011 | Idempotency API blocks both requests instead of just the duplicate | The idempotency mechanism incorrectly handles two identical answer requests sent concurrently: both are rejected with 409 Conflict, and neither answer is saved. | UC-11 | High | Nguyen Minh Phat | 2026-08-06 | Closed | The first request must be processed; only the duplicate request should be blocked or return the saved result.
B012 | Tooltip display error in Concept Graph | The tooltip showing concept details on the graph overflows its content and is overlapped by adjacent nodes, preventing users from reading the full information. | UC-17 | Low | Nguyen Minh Phat | 2026-08-07 | Closed | Need to limit the content and increase the z-index so the tooltip is not obscured.
B013 | Concept detail sidebar shows raw variable names instead of friendly labels | The Concept detail sidebar displays internal variable names instead of user-friendly labels, making the interface inconsistent with nodes on the graph. | UC-17 | Low | Nguyen Minh Phat | 2026-08-08 | Closed | Need to replace internal variable names with friendly labels, consistent with the interface.
B014 | Requests that lost claim rights still record results and advance the state machine | The command to claim a turn checks if the turn is still valid, but the commands to write score, feedback, and verdict only lock by id. Therefore, a request that has lost its claim can still overwrite the result and trigger a transition to the next question. | UC-11 | High | Nguyen The Quan | 2026-08-08 | Closed | Only requests holding a valid claim right should be allowed to record scores and change the session state.
B015 | Gemini calls have no timeout/AbortSignal and can hang indefinitely | GoogleGenAI is initialized without httpOptions timeout, and SDK calls do not pass AbortSignal. An unresponsive Gemini request will hang indefinitely, preventing the AE-02 retry and AE-05 Flashcard fallback from running. | UC-11 / UC-12 | High | Nguyen The Quan | 2026-08-09 | Closed | Need to add timeout and cancellation mechanisms so retries/fallbacks can always be triggered.
B016 | Vietnamese uploaded filenames turn into mojibake right upon saving to the database | Multer/busboy decodes file.originalname in latin1 instead of UTF-8. The corrupted filename is saved directly into Document.filename, making this a data error from the upload layer, not just a display issue. | UC-05 | Medium | Nguyen The Quan | 2026-08-09 | Closed | Need to configure UTF-8 encoding when receiving filenames and handle corrupted data separately.
B017 | Review queue and auto-pick do not filter out deprecated concepts | The resolvePlanQueue read path only filters ReviewQueueItem statuses, but not related concept statuses. A review item of a deprecated concept still appears in the queue and can be auto-picked to create an interview session on a concept that has been removed from the plan and graph. | UC-19 | High | Nguyen The Quan | 2026-08-13 | Closed | Need to filter out deprecated concepts at the read paths of the review queue.
B018 | Empty-state review queue shows incorrect message and CTA state | After the queue filters out deprecated concepts, a plan that already has interview results but where all previously scheduled concepts have been removed might fall into the fallback. The UI then incorrectly says the plan has no interview sessions/results. For plans with no active concepts left, the UI also displays congratulations and a CTA to start a session, leading to a 409 NO_CONCEPTS_TO_REVIEW error. | UC-19 | Medium | Nguyen The Quan | 2026-08-13 | Closed | Need to display appropriate messages and CTAs based on the revision history and graph state.
Note on D1: Function ID of the function where the defect is found
Note on E1: High, Medium, or Low
Note on F1: Name of the tester who reports the defect
Note on H1: Open or Closed