## Features
Project: Recall AI
Team: 7
ID | Feature Name | Description | Remark
FS-01 | Start Focus Session | Entry conditions, start/timer, completion, early end, pause/resume, strict mode, cancel, recovery, spam-click, handover.
FS-02 | Configure Learning Method | Pomodoro configuration (work/break/cycles/sound/strict mode) at session scope.
FS-04 | View Original Document in Session | Hide / Excerpt / Full Text document modes during a session.
FS-05 | Quick Notes in Session | Concept-linked quick notes, auto-save, and failure handling.
FS-06 | View Suggested Concepts | Focus reads the priority concept/reason from the review queue.

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01 (Focus Session): FS-01 - Start Focus Session
FS-01 | TC-FS-001 | Only show valid entry states and do not create a session before Start | Prerequisites: Primary learner has an active revision plan, a priority item pointing to the suggested concept; an unauthenticated client; a learner without an active plan. 1. Open Focus while unauthenticated. 2. Open Focus using a learner with no active plan. 3. Open Focus using the primary learner when the review queue returns a priority item pointing to the suggested concept. Input: a) No Bearer token. b) Review queue with no active plan. c) Review queue with first priority item = suggested concept. | a) Prompted to log in; no POST to create a session. b) Displays correct heading "You have no active revision plan." and CTA per mockup, no auto picker/session. c) Displays suggested concept with reason, default Pomodoro, "Choose another concept" option; no timer/Cancel/POST before Start. | a) PASS - Chromium+Firefox: route redirects to Login, no POST; API without token returns 401. b) PASS - displays correct heading/CTA, no Start button/POST/record. c) PASS - displays suggested concept, reason, 25:00, Dashboard link; no timer/Cancel/POST/record before Start. | PASS | Nguyễn Minh Phát | 2026-08-10 | The learner understands why they cannot start yet and has a clear next step, rather than being pushed into an empty session.
FS-01 | TC-FS-004 | Only create one session when the learner clicks Start, and timer runs correctly | Prerequisites: Primary learner is in the Not Started state with the suggested concept and valid Pomodoro configuration. 1. Send API request with empty conceptIds. 2. From UI, Start the suggested concept with Strict Mode on/off respectively. 3. Send API request with three concepts from the same plan and verify response/DB. Input: a) conceptIds=[]. b) Suggested concept of active plan, strictMode on/off. c) conceptIds = [three concepts from same plan]. | a) API returns 400 VALIDATION_ERROR, no record created. b) No record before Start; after Start, exactly one POST/running session for suggested concept, strictMode matches input, timer counts down. c) API creates exactly one session containing all three concepts from the same plan. | a) PASS - API returns 400 VALIDATION_ERROR, DB has no record. b) PASS - Strict on/off both emit exactly one POST, response/DB match, strictMode matches input, timer counts down. c) PASS - API creates exactly one session linking all three concepts. | PASS | Nguyễn Minh Phát | 2026-08-10 | Clear boundary before and after pressing Start helps prevent creating accidental sessions or studying the wrong concept.
FS-01 | TC-FS-007 | Pomodoro turn finishes naturally to a break; confirming completion generates correct summary time data | Prerequisites: A session for the suggested concept is running with a short test configuration. 1. Start the session. 2. Wait for the turn/cycle to complete naturally, without manually ending early during work turn. 3. On the long break screen, confirm 'End Session'. 4. Verify the summary and PATCH completion. Input: The suggested concept, a short Pomodoro test configuration. | End of turn naturally shifts to a long break without sending a PATCH; after confirmation, session marked completed exactly once. Summary shows focused time, number of Pomodoros, away count correctly; durationMinutes from focusedSeconds. Does not record mastery_score. | PASS - Chromium+Firefox: work turn naturally shifts to long break without PATCH; confirming on break screen issues exactly one completion, summary matches DB, masteryScore/lastTestedAt of studied concept remain unchanged. | PASS | Nguyễn Minh Phát | 2026-08-10 | Confirming completion before finalizing the session helps prevent users from accidentally recording false progress and makes the next step clear.
FS-01 | TC-FS-008 | Ending early only records actual focused time | Prerequisites: A session for the suggested concept is running. 1. End after a specific period of focused time. 2. Repeat after having paused/resumed or left the Strict Mode tab. 3. Verify the PATCH request and DB. Input: a) 65 seconds of focused time. b) 65 seconds of focused time including pause/away time. | Each session transitions to completed exactly once; focusedSeconds excludes pause/away time; durationMinutes = floor(focusedSeconds/60), summary matches DB. | a) PASS - Chromium+Firefox: 65 continuous seconds, one completion, durationMinutes=1, summary matches DB. b) PASS - Chromium+Firefox: 65 focused seconds with pause+away; wall-time interruption excluded, awayCount=1, payload/summary/DB all match. | PASS | Nguyễn Minh Phát | 2026-08-10 | Break times are not counted as study time, ensuring the statistics reflect real effort and remain trustworthy.
FS-01 | TC-FS-009 | Pause does not accumulate time and Resume continues the correct turn | Prerequisites: A session for the suggested concept is running. 1. Pause mid-turn and measure timer/focused time. 2. Keep it paused for a specific duration. 3. Resume, complete the session, verify the data. Input: a) Single pause. b) Two consecutive pause/resume cycles. | Focused timer does not decrease during pause; after Resume, the turn continues correctly; completion payload excludes all paused time. | a) PASS - Chromium+Firefox: single Pause/Resume freezes both clocks, continues correctly on Pomodoro 1/4, completion excludes paused time. b) PASS - Chromium+Firefox: two Pause/Resume cycles yield the same result; payload, summary, and DB match. | PASS | Nguyễn Minh Phát | 2026-08-10 | Pausing does not skew the session's progress, letting users comfortably return after brief interruptions.
FS-01 | TC-FS-012 | Strict Mode tracks time spent off-tab, does not fake browser locking | Prerequisites: Strict Mode enabled before Start; a session for the suggested concept is running. 1. Switch to another tab/app for a specific duration. 2. Return to Focus. 3. Choose either a) Continue, or b) Disable Strict Mode at the away panel, then complete the session. Input: a) Left once. b) Left multiple times. | Focused timer pauses during away time; UI explains duration/frequency of leaving; awayCount and focusedSeconds in completion match observations. "Disable strict mode" resumes timer with Strict off; app does not falsely claim to lock/block other tabs. | a) PASS - Chromium+Firefox: single away instance explains 3 seconds passed, timer/focused time paused, Strict locked, completion awayCount=1. b) PASS - two away instances accumulate count correctly; away CTA disables Strict for remainder of session, away time excluded, payload/summary/DB match. | PASS | Nguyễn Minh Phát | 2026-08-10 | Strict mode clearly explains excluded time when leaving a tab, establishing accountability without feeling arbitrarily punitive.
FS-01 | TC-FS-013 | Canceling a session requires confirmation and does not record time in history | Prerequisites: A session for the suggested concept is running and has accumulated focused time. 1. Select Cancel Session. 2. Try "Return to session". 3. Reopen the dialog and confirm Cancel Session. Input: The learning concept has focusedSeconds > 0. | The dialog clearly states time will not be recorded; returning leaves the session unchanged; confirmation sends a cancelled status, durationMinutes is 0, session not marked completed. | PASS - Chromium+Firefox: "Return to session" maintains the running session; confirming sends a cancelled payload with raw focusedSeconds, DB logs an audit with durationMinutes=0, no completed session created. | PASS | Nguyễn Minh Phát | 2026-08-10 | Canceling needs to be an intentional choice; learners are not penalized with false progress when deciding to stop mid-way.
FS-01 | TC-FS-016 | Sessions of 60 seconds or more can be recorded or discarded upon reopening | Prerequisites: A session for the suggested concept is running, localStorage snapshot contains focused time >= 60 seconds. 1. Close the tab/browser without Ending/Canceling. 2. Reopen the same browser context. 3. Choose sequentially a) Record, b) Discard in independent runs. Input: a) Record N minutes. b) Discard. | Recovery dialog shows the measured focused time. a) Correctly completes the old session exactly once, clears snapshot post-ACK. b) Does not create a completed session, clears snapshot, does not repeat the dialog. | a) PASS - Chromium+Firefox: dialog accurately reads snapshot >=60s; exactly one completion PATCH for old session, payload/DB match, snapshot cleared, reload does not loop. b) PASS - "Discard" creates no completed session, clears snapshot, does not prompt again. | PASS | Nguyễn Minh Phát | 2026-08-10 | After an interruption, learners have the agency to continue or drop the session, avoiding "ghost" sessions or repetitive prompts.
FS-01 | TC-FS-022 | Another learner cannot read or modify the primary learner's session | Prerequisites: The primary learner has one session; another learner has a distinct valid token. 1. The other learner issues a PATCH to the primary learner's session. 2. The other learner issues a GET for history. 3. Verify the response and DB. Input: The other learner's token; session ID belonging to the primary learner. | PATCH returns 404, does not expose the session, leaves the primary learner's session unchanged; the other learner's history contains no data/concepts belonging to the primary learner. | PASS - Chromium+Firefox: other learner's PATCH to primary learner's session yields 404/NOT_FOUND without exposing identifiers; history solely contains control data of the other learner; primary learner's session states remain completely unchanged. | PASS | Nguyễn Minh Phát | 2026-08-10 | Learners can trust that their history and sessions will not leak to other accounts.
FS-01 | TC-FS-023 | Spam clicking Start does not create duplicate sessions | Prerequisites: The primary learner is in the Not Started state for the suggested concept. 1. Click Start multiple times consecutively while the first request is still pending. 2. Wait for the request to settle. 3. Inspect the UI, network, and DB. Input: 3-5 consecutive clicks for the same suggested concept. | The UI disables/debounces the action early enough; only one running session is created for this click sequence, timer uses the correct response ID. | PASS - Chromium+Firefox: while the initial POST is pending, 5 independent mouse clicks render the button disabled/aria-busy; only one POST/record is generated for the suggested concept under the active plan; timer snapshot leverages the correct response ID. | PASS | Nguyễn Minh Phát | 2026-08-10 | Repeated clicks due to impatience or a slow network will not duplicate the session or corrupt progress tracking.
FS-01 | TC-FS-024 | Reloading under 60 seconds bypasses recovery prompts but must fully close the running record | Prerequisites: A session for the suggested concept is running; focused time is less than 60 seconds. 1. Start the session. If shortening time via the browser clock, wind back the start time in test data after creation so server time is not shorter than cleanup duration; run for 10-59 seconds. 2. Reload the page. 3. Inspect the UI and data immediately after reloading. Input: 10-59 seconds of focused time; page reload. | UI reverts to setup, shows no recovery dialog, creates no duplicate session. Old session closed as cancelled with durationMinutes=0 immediately upon abandonment, without waiting for an 8-hour lazy reap. | PASS - Chromium+Firefox: accurate UX (setup, no recovery dialog, no duplicate session creation); reload dispatches a PATCH cancelled for the old session, DB logs endedAt, durationMinutes=0, no running record remains. Re-verified PASS 2026-08-12 after fixing the short-session cleanup regression. | PASS | Nguyễn Minh Phát | 2026-08-10 | A very early refresh is treated as leaving the session, circumventing unintended recoveries and preventing duplicate sessions.
FS-01 | TC-FS-026 | Summary screen successfully hands over context to AI Examiner or Dashboard | Prerequisites: A session for the suggested concept is completed and the summary is displayed. 1. Select "Start test". 2. In an independent run, select "Maybe later - back to Dashboard". 3. Verify navigation and data. Input: A completed session for the suggested concept within the active plan. | a) CTA creates/opens an Interview using the suggested concept context, no concept re-selection required. b) Dashboard does not spawn a new Focus/Interview. c) Focus merely preserves time stats, without changing mastery_score. | a) PASS - Chromium+Firefox: CTA POSTs an Interview with the active plan/suggested concept, route uses response ID, opens directly to that concept without re-selection; mastery/lastTestedAt remain unaltered pre-scoring. b) PASS - returning to Dashboard creates no new Focus/Interview; assessment of the suggested concept remains immutable; Dashboard shows active plan. | PASS | Nguyễn Minh Phát | 2026-08-10 | Ending the session provides the learner with a transparent next step without forcing immediate testing.
Function 02 (Focus Session): FS-02 - Configure Learning Method
FS-02 | TC-FS-002 | Display default configuration and apply configuration at session scope correctly | Prerequisites: Primary learner is in the Not Started state for the suggested concept. 1. Observe default configuration. 2. Open panel from "Change turn duration", adjust work/short break/long break/cycles/sound and Strict Mode, then start. 3. While a turn is running, open the panel via config icon and change data. Input: a) Default 25/5/15/4, sound on. b) Another valid set of values. c) Change mid-turn. | a) Correctly displays all five fields; Strict Mode toggleable before Start. b) Changes apply only to the current session, no PATCH to user's default configuration. c) Current turn duration unchanged; new values apply at next turn boundary; Strict Mode locked until session end. | a) PASS - Chromium+Firefox: panel shows 25/5/15/4, sound, Strict Mode correctly. b) PASS - 1/2/3/2 config applies only to current session, no user config PATCH. c) PASS - changing mid-turn to 2/4/6/3, sound=false doesn't reset current turn; new values apply sequentially at next boundary, no chime, Strict locked, no user config PATCH. | PASS | Nguyễn Minh Phát | 2026-08-10 | The learner retains control over the ongoing session: mid-turn changes do not cause the clock or strict mode to shift unexpectedly.
Function 03 (Focus Session): FS-04 - View Original Document in Session
FS-04 | TC-FS-005 | Correctly switch document modes without disrupting the session | Prerequisites: A session for the suggested concept is running; the concept has a source citation and a valid PDF. 1. Select Hide, Excerpt, and Full Text sequentially. 2. Observe content, page anchor, and timer in each mode. Input: The suggested concept has a source page/excerpt; a readable PDF. | Each choice accurately reflects the selected state; Excerpt anchors to the concept's source, Full Text opens PDF to correct page; timer/session continues without creating a new session. | PASS - Chromium+Firefox: Hide/Excerpt/Full Text have correct selected-state; excerpt/filename/page anchor match DB source; PDF loads correct page; timer continues, no new session created. | PASS | Nguyễn Minh Phát | 2026-08-10 | Changing document detail levels does not break the learning rhythm or time tracking, suitable for when the learner needs quick references.
Function 04 (Focus Session): FS-05 - Quick Notes in Session
FS-05 | TC-FS-006 | Save notes to the correct concept without skewing the timer | Prerequisites: A session for the suggested concept is running and session_notes support is ready. 1. Open notes via the button and the 'N' key. 2. Create a new note, edit the note, close/reopen the rail. 3. Verify the saved data. Input: A new note containing valid content for the concept being studied. | Rail appears instantly as an overlay, timer does not shift/pause; new note auto-saved and reloaded for the correct session/concept with latest content. | PASS - Chromium+Firefox: rail opens via button/N, overlay doesn't skew/pause timer; POST/PATCH maintains exactly one note for session+concept, re-reads latest content upon remount. | PASS | Nguyễn Minh Phát | 2026-08-10 | Learners can note down sudden thoughts without fearing their latest edits will be lost or interrupt the session.
FS-05 | TC-FS-020 | Do not report successful save when quick note auto-save fails | Prerequisites: A session for the suggested concept is running, the notes rail is open. 1. Enter a new note. 2. Trigger a controlled auto-save request failure. 3. Observe the UI response and persistent data after closing/reopening the rail in the same session. Input: A new note; timeout or 5xx error for the save request. | UI does not assert the new note has been saved; reports appropriate error/retry state, retains the user's drafted content, does not break the timer. DB has no fake success record. | PASS - Chromium+Firefox: narrow fault injection returning 503 for POST note; UI displays "Save error - retry", does not report saved, retains new note across rail remounts; session timer continues, DB has no fake note. | PASS | Nguyễn Minh Phát | 2026-08-10 | If saving a note encounters an error, drafted content is preserved so learners do not get a false sense of success.
Function 05 (Focus Session): FS-06 - View Suggested Concepts
FS-06 | TC-FS-011 | Focus correctly uses the priority concept and reason from the review queue | Prerequisites: The review queue has a priority item pointing to the suggested concept, or returns an empty list along with a message. 1. Open Focus via the sidebar using the review queue's priority item. 2. Open Focus when the suggestion list is empty. 3. Follow the "Choose another concept" link. Input: a) items[0] is a priority item with a suggestion reason. b) items = []. | a) Displays the suggested concept/reason exactly per response, no new picker/list. b) Displays server message with Dashboard CTA, creates no session. c) Link navigates back to Dashboard before a session is created. | a) PASS - Chromium+Firefox: Focus calls limit=1, displays items[0] and reason from server intact, no picker. b) PASS - Chromium+Firefox: items=[] displays correct server message, two CTAs, no session created. c) PASS - "Choose another concept" navigates back to Dashboard before session creation; Dashboard shows active revision plan. | PASS | Nguyễn Minh Phát | 2026-08-10 | The suggestion reason and option to change concepts help learners understand their current choice rather than being forced into a vague recommendation.